## FAT-SAT checklist
FAT and SAT Checklist for Equipment from Japanese Suppliers
Free template from MONOSCOPE (monoscope-media.com/en/). Adjust items to your contract, equipment, and industry.
| Project: ____________________ | Supplier: ____________________ | Equipment: ____________
No | Item | Notes | Done (Y/N) | Checked by | Date | Comments
Before FAT
1 | Every requirement in the URS has a number, a measurement method, and test conditions | Replace words like "high speed" or "sufficient accuracy" with values that can pass or fail.
2 | Cycle time requirement states the part, the number of consecutive parts averaged, and whether changeover is included | Fictional example: Part A, 200 consecutive parts, average 12.0 s or less, changeover excluded.
3 | Continuous-run duration, allowed number of stops, and the definition of a stop are written in the spec | OEE's split into availability, performance, and quality is a useful model.
4 | Contract states what counts as kenshu (acceptance): FAT pass, SAT pass, or a run with production parts | Kenshu (検収): state how it relates to payment and the warranty start.
5 | Payment milestones, handling of open items, and warranty start date are agreed in writing | Align engineering and purchasing before the order is placed.
6 | Inspection procedure (kensa yoryo-sho, 検査要領書) received and reviewed | Check items, methods and instruments, acceptance criteria, test parts, FAT or SAT for each item, witnesses, and record format.
7 | Each test item is traced to a line in the specification | Items with no spec reference invite disputes on the day.
8 | Test parts agreed: production parts or substitutes, type, and quantity | Substitutes cannot show real production conditions.
9 | Production materials and parts scheduled to arrive at the supplier's factory before FAT | Allow time for international shipping to Japan.
10 | Document deliverables and languages listed in the PO | For example: inspection report, trial-run procedure, drawings, schematics, BOM, manual, spare parts list.
11 | Responsibility boundary (toriai, 取り合い) for utilities and signal interfaces defined | Power, compressed air, cooling water, exhaust, and signals to other equipment.
12 | FAT attendees confirmed: manufacturing engineering plus production, maintenance, and quality | Operators and maintenance staff spot usability and maintainability issues.
During FAT
13 | Build matches spec: device models, specified component brands, paint color, wiring and piping routing, nameplates
14 | Cycle time and machining or assembly accuracy measured on the specified parts | Record measured values, instruments, and sample count.
15 | Continuous run completed; every stop and its cause recorded
16 | Auto, manual, and changeover modes, I/O signals, and HMI screens checked
17 | Faults triggered on purpose (missed pick, undetected sensor, material out); cause shown on screen and recovery by procedure confirmed | Normal running in a demo proves little about production.
18 | Safety functions tested: E-stops, door interlocks, light curtains | What your plant requires is decided by your safety team and local regulations.
19 | Residual-risk list received, with an explanation of which hazards remain in which tasks | Starting point for your own risk assessment.
20 | Documents checked against the machine: drawings, schematics, BOM, manual, control program version, spare parts list
FAT sign-off
21 | Every finding recorded with a priority: fix before shipment / fix by SAT / fix later | Safety, quality, and legal-compliance items are fixed before shipment.
22 | Each finding has an owner and a due date | Write down verbal promises such as "We'll fix that" and have both sides confirm.
23 | Inspection report (kensa seiseki-sho, 検査成績書) with measured values signed by both sides
24 | Control program version recorded, and handling of post-FAT program changes agreed | Change history and scope of retest.
25 | Items that can rely on FAT results (not repeated at SAT) listed, with the reason | EU GMP Annex 15 allows this where transport and installation do not affect the function.
26 | Fixes due before shipment confirmed closed before release to ship
Before SAT
27 | Equipment photographed during uncrating | Evidence if shipping damage is disputed.
28 | Foundation, anchor positions, and leveling confirmed
29 | Plant utilities ready and within spec: supply voltage and capacity, compressed air pressure and flow, cooling water, exhaust | Check air pressure while other machines are running.
30 | Signal wiring to conveyors, neighboring equipment, and host systems connected
31 | Production materials, parts, and operators scheduled for the SAT runs
32 | SAT items in the inspection procedure confirmed, split into quick rechecks and on-site-only checks | Spend SAT time on what can only be checked on site.
During SAT
33 | Condition after shipping checked: scratches, deformation, loosening, wiring or piping damage
34 | Representative accuracy items from FAT remeasured | Shows whether a problem came from shipping or existed before.
35 | Signals, timing, and interlocked stops with other equipment tested
36 | Run with production materials and your own operators; capacity, quality, and changeover time confirmed
37 | Operator training and maintenance walkthrough (inspection and parts replacement) received | Feeds your maintenance plan.
Final acceptance
38 | All safety and quality items closed before acceptance
39 | Punch list (zanken list, 残件) signed by both sides with content, owner, due date, and how closure is confirmed
40 | Acceptance record signed and kenshu date recorded
41 | Payment milestone triggered as defined in the contract
42 | Warranty start confirmed: acceptance date or punch-list closure
43 | Governing law and contractual inspection period checked with legal or purchasing | Under Japanese law, Commercial Code Art. 526 expects prompt inspection and notice; contracts often set their own period.
44 | Final documents received in the agreed versions and languages | Revisions match the machine as installed.